Project Roadmap

Working Title

"Unsupervised Anomaly Detection for Predictive Maintenance in Industrial IoT Using Autoencoder and LSTM-Based Models"

―――――――――――――――――――――――――――――――――――――――――――――――――――――――

Research Timeline

| Phase | Description | Status | Dependencies |
| --- | --- | --- | --- |
| Phase 0 | Project Foundation & Environment Setup | ✅ Complete | None |
| Phase 1 | Literature Review & Research Landscape | 🔲 Pending | Phase 0 |
| Phase 2 | Research Gap Definition | 🔲 Pending | Phase 1 |
| Phase 3 | Dataset Acquisition & EDA | 🔲 Pending | Phase 0 |
| Phase 4 | Data Engineering Pipeline | 🔲 Pending | Phase 3 |
| Phase 5 | Baseline Implementation | 🔲 Pending | Phase 4 |
| Phase 6 | Autoencoder Implementation | 🔲 Pending | Phase 4 |
| Phase 7 | LSTM Autoencoder Implementation | 🔲 Pending | Phase 4 |
| Phase 8 | Anomaly Scoring & Thresholding | 🔲 Pending | Phases 5-7 |
| Phase 9 | Early Warning Framework | 🔲 Pending | Phase 8 |
| Phase 10 | Cross-Condition Experiments | 🔲 Pending | Phase 8 |
| Phase 11 | Ablation Studies | 🔲 Pending | Phase 8 |
| Phase 12 | Statistical Analysis | 🔲 Pending | Phases 10-11 |
| Phase 13 | Publication-Quality Figures & Tables | 🔲 Pending | Phase 12 |
| Phase 14 | Demonstration Dashboard | 🔲 Pending | Phase 8 |
| Phase 15 | Research Paper Draft | 🔲 Pending | Phase 13 |
| Phase 16 | BTech Thesis Draft | 🔲 Pending | Phase 15 |
| Phase 17 | Reproducibility & Validity Audit | 🔲 Pending | Phase 16 |

―――――――――――――――――――――――――――――――――――――――――――――――――――――――

Methodology Overview

Models Under Investigation

Statistical Threshold Baseline — Simple statistical anomaly detection (z-score / percentile)

Isolation Forest — Classical unsupervised anomaly detection

One-Class SVM — Kernel-based anomaly detection (if computationally feasible)

Fully Connected Autoencoder — Reconstruction-error-based anomaly detection

LSTM Autoencoder — Temporal reconstruction-error-based anomaly detection

Variational Autoencoder — Only if it adds genuine research value

Datasets

Primary: NASA C-MAPSS Turbofan Engine Degradation (FD001–FD004)

Secondary: To be determined based on research needs

Key Experimental Dimensions

Model comparison — Baseline vs. AE vs. LSTM-AE

Operating conditions — Single vs. multiple conditions (FD001 vs FD002/FD004)

Failure modes — Single vs. multiple fault modes (FD001 vs FD003/FD004)

Cross-engine generalization — Train/test on separate engines

Early warning capability — Detection lead time before failure

Threshold sensitivity — Effect of threshold strategy on detection quality

Complexity vs. performance — Is added model complexity justified?

―――――――――――――――――――――――――――――――――――――――――――――――――――――――

Hardware & Environment

OS: Windows 11 (x64)

CPU: Intel Core i7-1165G7 (4 cores, 8 threads)

RAM: ~16 GB

GPU: Intel Iris Xe Graphics (integrated — no CUDA)

Disk: ~106 GB free

Python: 3.10.7

Deep Learning: PyTorch 2.3.0+cpu

Hardware Implications

All training will run on CPU. This constrains model size and experiment count.

LSTM Autoencoder training may be slow — keep architectures moderately sized.

Batch experiments should use reasonable hyperparameter ranges, not exhaustive grid search.

Save checkpoints to avoid retraining.

―――――――――――――――――――――――――――――――――――――――――――――――――――――――

Risk Register

| Risk | Impact | Mitigation |
| --- | --- | --- |
| No GPU — slow training | Medium | Keep models small, use early stopping, cache results |
| C-MAPSS is synthetic data | Medium | Acknowledge in limitations, discuss implications |
| Overfitting on small engine count | Medium | Engine-level splits, report confidence intervals |
| Threshold sensitivity dominates results | High | Systematic threshold analysis, report across thresholds |
| Deep learning underperforms baselines | Low (risk to expectations) | Report honestly — this IS a valid finding |
| Disk space constraints | Low | Clean intermediate files, use compressed formats |

―――――――――――――――――――――――――――――――――――――――――――――――――――――――

Decision Log

| Date | Decision | Rationale |
| --- | --- | --- |
| 2026-10-02 | Use CPU-only PyTorch | No NVIDIA GPU available |
| 2026-10-02 | Start with FD001 | Simplest subset (1 operating condition, 1 fault mode) |
| 2026-10-02 | Engine-level data splits | Prevents temporal leakage across engines |
| 2026-10-02 | Configuration-driven experiments | Reproducibility and systematic variation |